## Sheet1
Stakeholder | Descriptor | Interest(s) in Project | Degree of importance | Potential Impact
(group) | (sector, business, etc.) | (areas of interest) | (none, minor, moderate, significant, unknown) | (negative, positive, neutral, unknown)
Search and Rescue | Public Safety | Search and Rescue | significant | Positive
Rokid | Business | Data Collection | minor | Unknown
Cal-Fire | Public Safety | Fire Prevention | minor | Positive
NASA Ames | Business | Data Collection | significant | Positive
Military | Government | Reconaissance | moderate | Positive
h-aero | Competitor | Decreased sales | minor | Negative
Drone manufacturers | Competitor | Decreased sales | minor | Negative
Elkaim/Mircea himself | Researcher | Collaberation in similar interest | moderate | Positive
Hobbyists | User | Personal use | minor | Positive
Surveyers | User/Research | Geographical Surveillance | moderate | Positive
Topologists | User/Research | Weather Monitoring | moderate | Positive
Questions
Purpose
What is the price range desired for the product in order to be feasible?
How long does the drone need to last? Does it need physical durability from potential interactions?
What are the weather conditions the drone needs to operate under?
Flight range
Environment
Plan
Client (NASA Ames) will provide the majority of answers to our questions, related to the specific needs of the drone
Reaserchers like Elkaim and Mircea can also answer more specific questions about the engineering process in creating the drone
The motive for communitcation with the client is to ensure the product we are delivering is meeting the clients needs and expectations.
The motive for communication with Elkaim and Mircea is to further our understanding of the topics we are less knowladgable of
Contact with Client on a weekly/Biweekly basis. Contact Elkaim and Mircea as needed
The most critcal stages for client input would be when the project is first started, at the end of the functional design phase, and at the end of the detailed design phase
We want to make sure that their requierments are matching up with the designs that we are creating. This requiers that they give us critical feedback, and helpful input from the client at each stage of the design process
Client will have a two-way discussion with our team and they will also be a end user. They will provide us with specific goals and feedback for our design
Elkaim and Mircea will have a one way interaction as a mentor too our group, providing us with knowladge in areas where we may lack
Interactions with stakeholders would include showing them our block diagram design (e.g. design method and procedure). Interview prompts will be prepared before every stakeholder meeting. During meetings we will take notes and have consensual recordings.