## Sheet1
Major Milestones | Dependencies | Resources | Deadline
1. Working Simulation of full scale drone | 0 | 1x | End of Winter
2. Full CAD model of drone | 1 | 1x | End of Winter
3. Fabrication and testing of small scale drone | 1,2,4,5,6,7 | 2x | End of Spring
4. Full PCB design | 0 | 1x | End of Winter
5. Embedded programming finished | 1 | 1x | End of Spring
6. Control systems programming finished | 0 | 1x | End of Winter
7. Power management completed | 4 | 1x | End of Spring